## Sheet1
Dates |  | Key Events |  | Tasks
Date | Uni Week | Stage | ProfDev Stage | Nathan | Joe | Josh | Kyle
2019-11-04 | Week 7 | Research | - | Look into AND make a simple test program using the APIs to understand how they work
2019-11-11 | Week 8 | Design | - | Design how the API's Will integrate together |  | Understand Pitch Critera
2019-11-18 | Week 9 | Design | - | Design how the API's Will integrate together |  | Work on Pitch
2019-11-25 | Week 10 | Working on Pitch | - | Implement API's |  | Work on Pitch
2019-12-02 | Week 11 | Working on Pitch | - | Implement API's |  | Work on Pitch
2019-12-09 | Week 12 | Working on Program | Pitch | Contribute to Pitch |  | Complete Pitch
2019-12-16 | Christmas | Working on Program | - | Start working on Main Project
2019-12-23 | Christmas | Working on Program | - | Work on Main Project
2019-12-30 | Christmas | Working on Program | - | Work on Main Project
2020-01-06 | Week 13 | Working on Program | - | Work on Main Project
2020-01-13 | Week 14 | Working on Program | - | Work on Main Project
2020-01-20 | Week 15 | Working on Program | - | Work on Main Project
2020-01-27 | Week 16 | Working on Program | - | Testing |  | Document Testing
2020-02-03 | Week 17 | Core Completed | - | Send Prototype to Arjun
2020-02-10 | Reading Week | Front end Design | -
2020-02-17 | Week 18 | Front end Design | -
2020-02-24 | Week 19 | Front End Work | -
2020-03-02 | Week 20 | Front End Work | -
2020-03-09 | Week 21 | Prepare Showcase | -
2020-03-16 | Week 22 | Prepare Showcase | Showcase
2020-03-23 | Week 23 |  | -
2020-03-30 | Week 24 |  | -